## Sheet1
Submission Details
Status | Accepted
Open Date | 2022-01-04
Deadline Date | 2022-01-31
Date Submitted | 2022-01-30
Type | Performance in Initiating
NHS provider | Essex Partnership University NHS Foundation Trust
Id | REC Number | IRAS System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
191943 | 20/LO/0894 | 272935 | DREAMS - A parallel multi-centre randomised controlled trial to determine the clinical and cost-effectiveness of DREAMS START (Dementia RElAted Manual for Sleep; STrAtegies for RelaTives)for people living with dementia and their carers | Yes | 2021-04-07 | 48 | 41 | 89 | 2020-07-24 | 2021-01-08 | 2020-09-18 | 2021-02-25 | 2021-02-25 | Please Select... | 2021-02-25 | J - Other | Equipment required to recruit participants was delayed | Sponsor
191944 | 20/LO/0034 | 274277 | The APPLE Tree programme: Active Prevention in People at risk of dementia through Lifestyle, bEhaviour change and Technology to build REsiliEnce: Pilot of the intervention and Randomised Controlled Trial | Yes | 2021-04-22 | 15 | 51 | 66 | 2021-02-01 | 2021-02-15 | 2020-03-02 | 2021-02-01 | 2021-03-02 | Please Select... | 2021-03-04 | J - Other | Sponsor does not consider participant a 'recruit' until they are randomised. This involves consent, several screening questionnaires and wearing an activity watch for 2 weeks prior to randomisation so this has had a significant impact on our timelines. We were not made aware of this during feasibility. Also, the sponsor closed during the Easter break for 2 weeks which caused significant delays in recruitment | Sponsor
191945 | 19/LO/1667 | 271363 | NIDUS -Clinical and cost-effectiveness of a New psychological intervention to support Independence in Dementia (NIDUS) for family carers and people living with dementia in their own homes: A randomised controlled trial | Yes | 2021-06-25 | 6 | 107 | 113 | 2021-03-04 | 2021-03-04 | 2020-01-13 | 2021-03-10 | 2021-03-10 | Please Select... | 2021-03-15 | F - No patients seen |  | NHS Provider
191946 | 19/NE/0233 | 239794 | PAX-BD - Randomised placebo controlled trial of Pramipexole addition to mood stabilisers for treatment resistant bipolar depression (the PAX-BD study) | Yes | 2021-11-26 | 48 | 177 | 225 | 2021-04-15 | 2021-04-15 | 2019-09-04 | 2021-05-26 | 2021-06-02 | Please Select... | 2021-06-23 | D - Sponsor Delays | Pending amendment to inclusion criteria in order to start recruitment. Patient must enrol in trial and be monitored for a minimum of 4 weeks before randomisation can occur. | Both
191947 | 19/LO/0088 | 257667 | SCENE WP5 - A randomised controlled trial of a structured intervention for expanding social networks in psychosis | Yes | 2021-07-27 | 1 | 5 | 6 | 2021-06-24 | 2021-07-21 | 2019-01-24 | 2021-07-22 | 2021-07-22 | Please Select... | 2021-07-23 |  |  | Please Select...